## Sheet1
Tasking Memory Analyzer Basic Project Plan
Steps | Duration(hours)
Discover the .map files | 5
Create a parsing strategy | 10
Create a coding architecture | 5
Parse and get required information | 10
Feature: Queriy mechanizm for variables and functions | 10
Feature: Memory usages of each module or unit. | 5
Feature: Memory usages of Rams and Flashes | 15
Feature: Memory usages of BSW, ISW, ASW, CAL sections | 15
Feature: Memory test(find wrong placed variables) | 10
Documentation | 15
TOTAL | 100
(2 Developer) x (5 hours) = 10 hours per week 100/10 = 10 week